## 2018 entry
For September 2018 Entry | 2016-09-01 | 2016-10-01 |  | 2016-11-01 | 2016-12-01 | 2017-01-01 |  | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01
UG | [5 empty] | Deadline for course changes - 2 weeks before print deadline | Changes to UG Entry Requirements in WPM are not advised. Any changes made on WPM must also be advised to coursechanges@manchester.ac.uk | 2017-05-01: UCAS Apply 2018 is now live - changes to course titles or entry requirements are not advised.
Undergraduate Pocket Guide |  | Fiona Eccles and Heidi Page to agree guidance for Schools - 4 Oct | Schools asked to rollover UG marketing data and update entry requirements on WPM - email w/b 14 Oct |  | Deadline for A level and IB entry requirements - 2 December |  | Print Delivery | 2017-03-01: First UCAS Fairs for 2018 entry
UCAS Entry requirements guide | [5 empty] | Deadline for additional entry requirements on WPM - 11 Jan | Admissions extract and format entry requirements data for guide | 2017-02-01: Print Delivery
Undergraduate Prospectus |  |  |  | Schools and central teams proofing UG prospectus |  |  |  | 2017-02-01: Print Delivery
Deadline for A level and IB entry requirements - 2 December Admissions run export for Student Marketing & Comms
International Undergraduate Prospectus |  |  |  | Schools and central teams proofing UG international prospectus
University UG Course Search | Switch off 2016 course listings |  |  |  |  | Deadline for additional entry requirements on WPM - 11 Jan |  | 2017-03-01: University website go live - 1 March; 2017-09-01: Switch off 2017 course listings
UCAS Course Search | [5 empty] | Deadline for additional entry requirements on WPM - Wednesday of the second week of Jan UCAS UG Collect live for 2018 entry |  | 2017-02-01: Admissions extract from WPM and update UCAS UG Collect; 2017-05-01: UCAS UG Search go live - early May UCAS Apply go live - late May; 2017-09-01: Applications for 2018 entry start to be submitted.
Extra & Clearing Listings (for 2017 entry) | [5 empty] | Admissions check open/closed courses for Extra with Schools |  | 2017-02-01: Extra opens - last week of February; 2017-06-01: Vacancy listing provided on Sharepoint mid-June. Schools & Faculty IMG reps required to check Clearing vacancies by end-June.; 2017-07-01: Clearing vacancies go live early July.; 2017-08-01: Deadline for listings for Telegraph - Monday of Clearing week. Notification of any further changes to Clearing vacancies following IMG meeting 12 noon on Tuesday of Clearing week. Further vacancy changes from 8am on results day need to be sent to coursechanges@manchester.ac.uk
UTT Course Listings |  | UTT course search live | [5 empty] | 2017-05-01: UTT course data rollover late May
PG
Postgraduate Prospectus | [7 empty] | 2017-03-01: Upload listings to Sharepoint for updating by Schools and teams; 2017-04-01: Schools and central teams proofing PG prospectus; 2017-06-01: Final sign off from stakeholders; 2017-07-01: Print Delivery
[10 empty] | Text editing and proofing process Design concepts | PDFs to contributors Schools update course info on WPM
University PG Course Search (2017 entry) | University 2017 PG listings go live - 26 Sept Switch off 2016 | [6 empty] | 2017-07-01: Schools/Faculty Marketing contacts asked to update PG marketing data in WPM - mid-July; 2017-09-01: University 2018 PG listings go live - 25 Sept Switch off 2017
UCAS PG Course Search & other external listings (2017 entry) |  | Admissions extract from WPM and update UCAS PG Collect and external listings

## 2017 entry
For September 2017 Entry | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 |  | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01
Changes to UG Entry Requirements in WPM are not advised. Any changes made on WPM must also be advised to coursechanges@manchester.ac.uk | bar: 2016-02-01 to 2016-04-01
Undergraduate Pocket Guide |  | Course listings from WPM proofing (taken from updates schools do for prospectus) | Final sign off from stakeholders | Print Delivery
UCAS Entry requirements guide | Schools asked to update A level and IB entry requirements on WPM | Deadline for A level and IB entry requirements - 18 November | Schools asked to update additional entry requirements on WPM | 11 Jan - deadline for additional entry requirements All WPM information updated Export from Campus Solutions |  | 2016-02-01: Student Recruitment sign off / Print / Delivery - mid Feb
Admissions extract and format entry requirements data for guide | bar: 2016-02-01
Undergraduate Prospectus | Schools asked to update A level and IB entry requirements on WPM | Schools and central teams proofing UG prospectus |  |  |  | 2016-02-01: Print Delivery
|  | Deadline for A level and IB entry requirements - 18 November Admissions run export for Student Marketing & Comms | Schools asked to update additional entry requirements on WPM Deadline for course changes - 2 weeks before prospectus deadline. | 11 Jan - deadline for additional entry requirements All WPM information updated Export from Campus Solutions | bar: 2016-02-01
International Undergraduate Prospectus | Schools asked to update A level and IB entry requirements on WPM | Deadline for A level and IB entry requirements - 18 November | Schools asked to update additional entry requirements on WPM | 11 Jan - deadline for additional entry requirements All WPM information updated Export from Campus Solutions |  | 2016-02-01: Print Delivery
University Course Search | Schools asked to update A level and IB entry requirements on WPM | Deadline for A level and IB entry requirements - 18 November | Schools asked to update additional entry requirements on WPM |  |  | 2016-02-01: University website go live first week of Feb | When does WPM roll over for UG?
UCAS Course Search | Schools asked to update A level and IB entry requirements on WPM | UCAS Course Data rollover | Schools asked to update additional entry requirements on WPM | 11 Jan - deadline for additional entry requirements All WPM information updated Export from Campus Solutions |  | 2016-02-01: Admissions extract from WPM and update UCAS Course Collect; 2016-05-01: UCAS Course Search go live - early May UCAS Apply go live - 23 May; 2016-09-01: Applications for 2017 entry start to be submitted.
Extra & Clearing Listings | [5 empty] | 2016-02-01: Extra opens - last week of February; 2016-06-01: Vacancy listing provided on Sharepoint mid-June. Schools & Faculty IMG reps required to check Clearing vacancies by 27 June.; 2016-07-01: Clearing vacancies go live early July.; 2016-08-01: Deadline for listings for Telegraph - Monday of Clearing week. Notification of any further changes to Clearing vacancies following IMG meeting 12 noon on Tuesday of Clearing week. Further vacancy changes from 8am on results day need to be sent to coursechanges@manchester.ac.uk
Postgraduate Prospectus | [5 empty] | 2016-03-01: Upload to Sharepoint for updating by Schools and teams; 2016-04-01: Schools and central teams proofing PG prospectus; 2016-06-01: Final sign off from stakeholders; 2016-07-01: Print Delivery | When does WPM roll over for PG? When does the PG web listing go live?
[8 empty] | Text editing and proofing process Design concepts | PDFs to contributors Schools update course info on WPM
UCAS PG Course Search
UTT Course Listings | [5 empty] | 2016-05-01: Rollover 24 May